## Sorted
Assignee | Sprint | Status | Item | Time | Time | Value | Value | Description | Score | Value / Hour | Comments
Matt Kearney | May 2-6 | Not Started | Colour Scheme Selection | 13 | a couple of hours | 13 | nominal | helps us move forward in long term goal | 1 | 0.15385
Justen DePourcq | May 2-6 | Not Started | Create Basic Webpage | 20 | half a day | 13 | nominal | helps us move forward in long term goal | 1.5385 | 0.1
Braden D'Eith | May 2-6 | Not Started | Create Basic Webpage 2 | 20 | half a day | 13 | nominal | helps us move forward in long term goal | 1.5385 | 0.1
Braden D'Eith | May 2-6 | Not Started | Presentation Slides | 13 | a couple of hours | 55 | necessary | current or potential customer want it | 0.23636 | 0.30769
Justen DePourcq | May 2-6 | Not Started | Presentation Slides 2 | 13 | a couple of hours | 55 | necessary | current or potential customer want it | 0.23636 | 0.30769
Matt Kearney | May 2-6 | Not Started | Design first level | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727
Mark Tattrie | May 2-6 | Not Started | Design first level 2 | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727
Braden D'Eith | May 2-6 | Not Started | Design first level 3 | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727
Karl Arreola | May 2-6 | Not Started | Design first level 4 | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727
Justen DePourcq | May 2-6 | Not Started | Design first level 5 | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727
Mark Tattrie | May 2-6 | In Progress | POP creation | 13 | a couple of hours | 20 | important | makes us stand out from our competitors | 0.65 | 0.23077
Matt Kearney | May 2-6 | In Progress | Main StoryBoard | 20 | half a day | 89 | critical | could cost us business | 0.22472 | 0.3
Karl Arreola | May 2-6 | Not Started | Gameplay StoryBoard | 89 | a day | 89 | critical | could cost us business | 1 | 0.067416
Mark Tattrie | May 2-6 | Not Started | Gameplay StoryBoard 2 | 89 | a day | 89 | critical | could cost us business | 1 | 0.067416

## Backlog
Assignee | Sprint | Status | Item | Time | Time | Value | Value | Description | Score | Value / Hour | Comments
Matt Kearney | May 2-6 | In Progress | Main StoryBoard | 20 | half a day | 89 | critical | could cost us business | 0.22472 | 0.3
Karl Arreola | May 2-6 | Not Started | Gameplay StoryBoard | 89 | a day | 89 | critical | could cost us business | 1 | 0.067416
Mark Tattrie | May 2-6 | Not Started | Gameplay StoryBoard 2 | 89 | a day | 89 | critical | could cost us business | 1 | 0.067416
Justen DePourcq | May 2-6 | Not Started | Create Basic Webpage | 20 | half a day | 13 | nominal | helps us move forward in long term goal | 1.5385 | 0.1
Braden D'Eith | May 2-6 | Not Started | Create Basic Webpage 2 | 20 | half a day | 13 | nominal | helps us move forward in long term goal | 1.5385 | 0.1
Matt Kearney | May 2-6 | Not Started | Colour Scheme Selection | 13 | a couple of hours | 13 | nominal | helps us move forward in long term goal | 1 | 0.15385
Braden D'Eith | May 2-6 | Not Started | Presentation Slides | 13 | a couple of hours | 55 | necessary | current or potential customer want it | 0.23636 | 0.30769
Mark Tattrie | May 2-6 | In Progress | POP creation | 13 | a couple of hours | 20 | important | makes us stand out from our competitors | 0.65 | 0.23077
Matt Kearney | May 2-6 | Not Started | Design first level | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727
Justen DePourcq | May 2-6 | Not Started | Presentation Slides 2 | 13 | a couple of hours | 55 | necessary | current or potential customer want it | 0.23636 | 0.30769
Mark Tattrie | May 2-6 | Not Started | Design first level 2 | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727
Braden D'Eith | May 2-6 | Not Started | Design first level 3 | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727
Karl Arreola | May 2-6 | Not Started | Design first level 4 | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727
Justen DePourcq | May 2-6 | Not Started | Design first level 5 | 55 | a few hours | 55 | necessary | current or potential customer want it | 1 | 0.072727

## Time
Item | Time | Description
Main StoryBoard | L | half a day
Gameplay StoryBoard | XXL | a day
Gameplay StoryBoard 2 | XXL | a day
Create Basic Webpage | L | half a day
Create Basic Webpage 2 | L | half a day
Colour Scheme Selection | M | a couple of hours
Presentation Slides | M | a couple of hours
POP creation | M | a couple of hours
Design first level | XL | a few hours
Presentation Slides 2 | M | a couple of hours
Design first level 2 | XL | a few hours
Design first level 3 | XL | a few hours
Design first level 4 | XL | a few hours
Design first level 5 | XL | a few hours

## Value
Item | Value | Description
Main StoryBoard | XXL | critical
Gameplay StoryBoard | XXL | critical
Gameplay StoryBoard 2 | XXL | critical
Create Basic Webpage | M | nominal
Create Basic Webpage 2 | M | nominal
Colour Scheme Selection | M | nominal
Presentation Slides | XL | necessary
POP creation | L | important
Design first level | XL | necessary
Presentation Slides 2 | XL | necessary
Design first level 2 | XL | necessary
Design first level 3 | XL | necessary
Design first level 4 | XL | necessary
Design first level 5 | XL | necessary

## Values
SIze | Points | Position | Time (Hours) | Time (Days) | Time (English) | Value (English) | Value Description
epic | 1000 | 8 | 6000 | 1000 | too big to say | too big to say | too big to say
L | 20 | 5 | 3 | 0.5 | half a day | important | makes us stand out from our competitors
M | 13 | 4 | 2 | 0.33333 | a couple of hours | nominal | helps us move forward in long term goal
S | 5 | 3 | 1 | 0.16667 | an hour | desirable | people would appreciate it
XL | 55 | 6 | 4 | 0.66667 | a few hours | necessary | current or potential customer want it
XS | 3 | 2 | 0.5 | 0.083333 | half an hour | trivial | people wouldn't notice it much
XXL | 89 | 7 | 6 | 1 | a day | critical | could cost us business
XXS | 1 | 1 | 0.2 | 0.033333 | a few minutes | silly | nobody cares
ZZZ | 0 | 0 | 0 | 0 | not estimated | not estimated | not estimated
Hours / Day | 6
Days / Week | 5

## Cheat Sheet
SIze | Points | Position | Time (Hours) | Time (Days) | Time (English) | Value (English) | Value Description |  | Time | Value |  |  | Score | Value / Hour
ZZZ | 0 | 0 | 0 | 0 | not estimated | not estimated | not estimated |  | XXS | XXL | 1 | 89 | 0.011236 | 6 | a few minutes | critical | could cost us business
XXS | 1 | 1 | 0.2 | 0.033333 | a few minutes | silly | nobody cares |  | XXS | XL | 1 | 55 | 0.018182 | 4 | a few minutes | necessary | current or potential customer want it
XS | 3 | 2 | 0.5 | 0.083333 | half an hour | trivial | people wouldn't notice it much |  | XXS | L | 1 | 20 | 0.05 | 3 | a few minutes | important | makes us stand out from our competitors
S | 5 | 3 | 1 | 0.16667 | an hour | desirable | people would appreciate it |  | XS | XXL | 3 | 89 | 0.033708 | 2 | half an hour | critical | could cost us business
M | 13 | 4 | 2 | 0.33333 | a couple of hours | nominal | helps us move forward in long term goal |  | XXS | M | 1 | 13 | 0.076923 | 2 | a few minutes | nominal | helps us move forward in long term goal
L | 20 | 5 | 3 | 0.5 | half a day | important | makes us stand out from our competitors | bring us up to our competitors | XS | XL | 3 | 55 | 0.054545 | 1.3333 | half an hour | necessary | current or potential customer want it
XL | 55 | 6 | 4 | 0.66667 | a few hours | necessary | current or potential customer want it |  | S | XXL | 5 | 89 | 0.05618 | 1.2 | an hour | critical | could cost us business
XXL | 89 | 7 | 6 | 1 | a day | critical | could cost us business |  | XS | L | 3 | 20 | 0.15 | 1 | half an hour | important | makes us stand out from our competitors
[9 empty] | XXS | S | 1 | 5 | 0.2 | 1 | a few minutes | desirable | people would appreciate it
[9 empty] | S | XL | 5 | 55 | 0.090909 | 0.8 | an hour | necessary | current or potential customer want it
[9 empty] | XS | M | 3 | 13 | 0.23077 | 0.66667 | half an hour | nominal | helps us move forward in long term goal
[9 empty] | S | L | 5 | 20 | 0.25 | 0.6 | an hour | important | makes us stand out from our competitors
[9 empty] | XXS | XS | 1 | 3 | 0.33333 | 0.5 | a few minutes | trivial | people wouldn't notice it much
[9 empty] | M | XXL | 13 | 89 | 0.14607 | 0.46154 | a couple of hours | critical | could cost us business
[9 empty] | S | M | 5 | 13 | 0.38462 | 0.4 | an hour | nominal | helps us move forward in long term goal
[9 empty] | XS | S | 3 | 5 | 0.6 | 0.33333 | half an hour | desirable | people would appreciate it
[9 empty] | M | XL | 13 | 55 | 0.23636 | 0.30769 | a couple of hours | necessary | current or potential customer want it
[9 empty] | L | XXL | 20 | 89 | 0.22472 | 0.3 | half a day | critical | could cost us business
[9 empty] | M | L | 13 | 20 | 0.65 | 0.23077 | a couple of hours | important | makes us stand out from our competitors
[9 empty] | L | XL | 20 | 55 | 0.36364 | 0.2 | half a day | necessary | current or potential customer want it
[9 empty] | S | S | 5 | 5 | 1 | 0.2 | an hour | desirable | people would appreciate it
[9 empty] | XXS | XXS | 1 | 1 | 1 | 0.2 | a few minutes | silly | nobody cares
[9 empty] | XS | XS | 3 | 3 | 1 | 0.16667 | half an hour | trivial | people wouldn't notice it much
[9 empty] | M | M | 13 | 13 | 1 | 0.15385 | a couple of hours | nominal | helps us move forward in long term goal
[9 empty] | L | L | 20 | 20 | 1 | 0.15 | half a day | important | makes us stand out from our competitors
[9 empty] | XL | XXL | 55 | 89 | 0.61798 | 0.10909 | a few hours | critical | could cost us business
[9 empty] | L | M | 20 | 13 | 1.5385 | 0.1 | half a day | nominal | helps us move forward in long term goal
[9 empty] | S | XS | 5 | 3 | 1.6667 | 0.1 | an hour | trivial | people wouldn't notice it much
[9 empty] | M | S | 13 | 5 | 2.6 | 0.076923 | a couple of hours | desirable | people would appreciate it
[9 empty] | XL | XL | 55 | 55 | 1 | 0.072727 | a few hours | necessary | current or potential customer want it
[9 empty] | XXL | XXL | 89 | 89 | 1 | 0.067416 | a day | critical | could cost us business
[9 empty] | XS | XXS | 3 | 1 | 3 | 0.066667 | half an hour | silly | nobody cares
[9 empty] | XL | L | 55 | 20 | 2.75 | 0.054545 | a few hours | important | makes us stand out from our competitors
[9 empty] | L | S | 20 | 5 | 4 | 0.05 | half a day | desirable | people would appreciate it
[9 empty] | XXL | XL | 89 | 55 | 1.6182 | 0.044944 | a day | necessary | current or potential customer want it
[9 empty] | S | XXS | 5 | 1 | 5 | 0.04 | an hour | silly | nobody cares
[9 empty] | M | XS | 13 | 3 | 4.3333 | 0.038462 | a couple of hours | trivial | people wouldn't notice it much
[9 empty] | XL | M | 55 | 13 | 4.2308 | 0.036364 | a few hours | nominal | helps us move forward in long term goal
[9 empty] | XXL | L | 89 | 20 | 4.45 | 0.033708 | a day | important | makes us stand out from our competitors
[9 empty] | L | XS | 20 | 3 | 6.6667 | 0.025 | half a day | trivial | people wouldn't notice it much
[9 empty] | XXL | M | 89 | 13 | 6.8462 | 0.022472 | a day | nominal | helps us move forward in long term goal
[9 empty] | XL | S | 55 | 5 | 11 | 0.018182 | a few hours | desirable | people would appreciate it
[9 empty] | M | XXS | 13 | 1 | 13 | 0.015385 | a couple of hours | silly | nobody cares
[9 empty] | XXL | S | 89 | 5 | 17.8 | 0.011236 | a day | desirable | people would appreciate it
[9 empty] | L | XXS | 20 | 1 | 20 | 0.01 | half a day | silly | nobody cares
[9 empty] | XL | XS | 55 | 3 | 18.3333 | 0.0090909 | a few hours | trivial | people wouldn't notice it much
[9 empty] | XXL | XS | 89 | 3 | 29.6667 | 0.005618 | a day | trivial | people wouldn't notice it much
[9 empty] | XL | XXS | 55 | 1 | 55 | 0.0036364 | a few hours | silly | nobody cares
[9 empty] | XXL | XXS | 89 | 1 | 89 | 0.0022472 | a day | silly | nobody cares

## Scrum
Name | Start | End | Status | Members
May 2-6 | 2016-05-02 | 2016-05-06 | Not Started | Matt Kearney
May 9-13 | 2016-05-09 | 2016-05-13 | In Progress | Mark Tattrie
May 16-20 | 2016-05-16 | 2016-05-20 | In Review | Braden D'Eith
May 24-27 | 2016-05-24 | 2016-05-27 | Done | Karl Arreola
Justen DePourcq